## User stories
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Owner | Apurva Kedar 23796845
As a user, I want:
|  | No | User stories | Week 2 | Week 3 | Week 4
|  | 1 | to create the snake game | Done
|  | 2 | The game board looks like : a) The background color is black b) The snake color is green c) The apple color is red d) The default board size is 900px by 900px | Done
|  | 3 | Print snake and prey as per given interface. a) Draw the Prey b) Draw the Snake c) Implement Layout Managers to show GUI as given in the assessment. d) Open Login Form on game start and show the Game Interface only on successful Login. |  | Done
|  | 4 | The board generates apples at random locations.
|  | 5 | The snake size is increased if the snake head touches the apple and then the board generates another apple at random position.
|  | 6 | The game is over if Snake Body hits the boundaries of the board and a message is displayed to the player.

## Snake-game
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Developer | Your name and student ID
No | Level-1 tasks | Level-2 tasks | Level-3 tasks | Priority | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Note
1 | Create a repository for the project on GitHub |  |  | 1 | 100%
2 | Create and update product backlog |  |  | 1 | 100%
3 | Build the snake game as in the product backlog |  |  | 2
3.1 |  | Build the GUI
3.1.1 |  |  | GUI for gameboard
3.1.2 |  |  | GUI for login form
3.2 |  | Build the game logic
3.2.1 |  |  | Snake logic
4 | Test and deploy the game |  |  | 3 | 0%
5 | Document the game |  |  | 4 | 0%