## User stories
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Owner | Apurva Kedar 23796845
As a user, I want:
|  | No | User stories
|  | 1 | to create the snake game
|  | 2 | the game board looks like : a) the background color is black b) the snake color is green c) the apple color is red d) the default board size is 400px by 400px
|  | 3 | Show the snake. The snake head looks like a pre loaded image and snake can move in upward, downward, left, right directions based on user inputs of respective arrow keys
|  | 4 | The board generates apples at random locations.
|  | 5 | The snake size is increased if the snake head touches the apple and then the board generates another apple at random position.
|  | 6 | The game is over if Snake Body hits the boundaries of the board and a message is displayed to the player.

## Snake-game
PROJECT | SNAKE GAME
Start | Week 8
End | Week 13
Developer | Your name and student ID
No | Level-1 tasks | Level-2 tasks | Level-3 tasks | Priority | Week 8 | Week 9 | Week 10 | Week 11 | Week 12 | Week 13 | Note
1 | Create a repository for the project on GitHub |  |  | 1 | 100%
2 | Create and update product backlog |  |  | 1 | 100%
3 | Build the snake game as in the product backlog |  |  | 2
3.1 |  | Build the GUI
3.1.1 |  |  | GUI for gameboard
3.1.2 |  |  | GUI for login form
3.2 |  | Build the game logic
3.2.1 |  |  | Snake logic
4 | Test and deploy the game |  |  | 3 | 0%
5 | Document the game |  |  | 4 | 0%